## Sheet1
Risk Assessment
| Project Name: | Delta-Cinema |  | Updated By: | Justin Graham |  |  | Last Updated: | 2022-09-07
|  |  |  | Inherent Risk (without controls) |  |  |  |  | Residual Risk (with controls) |  |  | Risk Matrix
Risk ID | Risk Descriptrion | Consequences | Risk Owner(s) Name and Role | Probability | Impact | Risk rating | Control(s) | Control Owner(s) Name and Role | Residual Probability | Residual Impact | Residual Risk Rating | Impact: |  | Very Low | Low | Medium | High | Very High | Probability | Impact
1 | New to group projects using GitHub | Could come into merge conflicts that prevent workflow until resolved | Team | High | High | Critical | Set up reviews and protections so that we minimise these risks | Team | Low | Low | Sustainable | Probability | Very High | Moderate | Severe | Severe | Critical | Critical | Very High | Very High
2 | New to programming Language | May add time to project as first time for all using the language in a project | Team | Very High | Very High | Critical | Review all material, research as much as possible, practice | Team | Medium | Medium | Moderate |  | High | Sustainable | Moderate | Severe | Critical | Critical | High | High
3 | Gathered data from users needs to be secure | User data could be stolen and used maliciously, could be sued | Team | High | Medium | Severe | Protect all data taken from users. Only store essentials. | Team | Low | Medium | Moderate |  | Medium | Sustainable | Moderate | Moderate | Severe | Critical | Medium | Medium
4 | New to React library | Could become a blocker and delay us, first time applying to a project | Team | High | High | Critical | Review all materials, practice methods before implementing | Team | Medium | Medium | Moderate |  | Low | Sustainable | Sustainable | Moderate | Severe | Critical | Low | Low
5 | Age restricted movies | Children could book films with age ratings above their age | Team | Very High | Very High | Critical | User must create account and enter their age, this will be checked | Team | Very Low | Very Low | Sustainable |  | Very Low | Sustainable | Sustainable | Sustainable | Moderate | Severe | Very Low | Very Low